## Run 1
# | Check | Action through REST API server | API result | Database check through MySQL server | Status
1 | Reset to seed data | POST /test/reset with X-Reset-Key | 200 {status: reset} | 30 products, 2 users, 0 orders, 0 cart rows, 0 tokens; category counts match GET /categories | Pass
2 | Passwords are stored hashed | (none) | (none) | users.password_hash is 64 hex characters, not the plain password | Pass
3 | Login | POST /auth/login for alice and bob | 200 with a token each | 2 rows in tokens | Pass
4 | Add to cart | POST /cart/items product 10 x2 | 200, subtotal 1298 | cart_items has user 1, product 10, quantity 2; stock of product 10 still 2 (cart does not reserve stock) | Pass
5 | Cannot exceed stock | POST /cart/items product 10 x1 more | 409 Only 2 in stock | cart quantity still 2 | Pass
6 | Second product | POST /cart/items product 5 x1 | 200, subtotal 1797 | cart rows p10x2, p5x1; bob has 0 cart rows | Pass
7 | Valid coupon | POST /coupons/validate welcome10 | 200 discount 179, total 1618 | (read only) | Pass
8 | Expired coupon | POST /coupons/validate EXPIRED50 | 400 Coupon has expired | (read only) | Pass
9 | Search treats % literally (MySQL) | GET /products?q=%25 | 200, products 5 and 26 only (their specs contain %) | (read only) | Pass
10 | Checkout | POST /checkout with card, coupon and shipping | 201 order 1: subtotal 1797, discount 179, total 1618, paid | orders row matches the API; order_items p10:649x2, p5:499x1 sum 1797; shipping JSON has PIN 560001; stock 10: 2 to 0, stock 5: 50 to 49; alice cart empty | Pass
11 | Second checkout of the same cart | POST /checkout again | 400 Cart is empty | still 1 order | Pass
12 | Another user cannot see or cancel the order | GET /orders/1 and POST /orders/1/cancel as bob | 404 for both | order 1 still belongs to user 1, status paid | Pass
13 | Cancel order | POST /orders/1/cancel as alice | 200 status cancelled | orders.status cancelled; stock 10 back to 2, stock 5 back to 50 | Pass
14 | Cancel twice | POST /orders/1/cancel again | 409 Order is already cancelled | stock unchanged (2 and 50) | Pass
15 | Logout ends the session | POST /auth/logout then GET /me with the old token | 200 logged out, then 401 Invalid token | alice has 0 token rows; bob still has 1 | Pass
16 | Order time is reported consistently | Compare created_at from POST /checkout and from POST /orders/1/cancel | Checkout said 2026-10-10T04:00:04.557361; the later response said 2026-10-10T04:00:05 | orders.created_at is DATETIME with no fractional seconds, so MySQL rounded the time up to the next second | FAIL
17 | Huge id and suggestions | GET /products/10^30 and GET /products/suggest?q=mob | 422 for the huge id; suggest returns Mobiles and products 9, 11, 15 | (read only) | Pass